## Sheet1
|  | Manager | Assistant 1 | Assistant 2 | Due date | Ahmet
| Report Component |  |  |  |  | Brandon
| Team Profile |  |  |  |  | Hugo
| Team Name |  |  |  |  | Taylen
1 | Organise the team to decide a Team name |  |  |  |  | Tim
| Personal information |  |  |  |  | Tetsu
2 | Obtain and summarise one paragraph per person including name, student number, background, hobbies, IT interest and IT experience
Team profile
3 | Obtain and summarise the test outcomes for each person in the team (all 3 tests)
4 | Summarise our understanding of how this information may be helpful to the group
Ideal Jobs
5 | Compare and Contrast the ideal jobs for each person in the group
Tools
7 | Decide the basic style, format and layout of the website and share with the group
8 | Put the website together and submit it as our website for the assignment
9 | Create links to each individual website on the group website
10 | Set up group in Canvas
11 | Set up a GitHub repository for the group
12 | Include a brief description of what we have done in the report
Industry Data
13 | Read (and ask the team to read) industry data supplied by Burning Glass and obtain the feedback
14 | Determine the job titles for our group's ideal jobs
15 | Summarise and report set of skills required for these jobs
16 | Write in our report if our opinion of ideal job changed? Why or Why not?
IT Work
17 | Decide to interview an IT Professional or pick 10 YouTube videos or web sources
18 | Organise and prepare for an interview
19 | Record an interview
20 | Include raw transcripts/recordings in appendix to support our written component
21 | Report on 5 different IT professions as well as indicate 10 sources
IT Technologies
22 | Report on 4 of the areas (1,200 words @ 3 = 3,600 words)
Project ideas
23 | Discuss, determine and brainstorm the group's project idea
24 | Write the result in our report
Feedback-SparkPLUS
25 | Supervise members to log in SparkPlUS Tool
26 | Supervise members to complete feedback
Group Reflection
28 | Supervise and obtain each member's perception of the group (200 words each)
29 | Write the group reflection as a whole (400 words)
Completion
30 | Proof reading
31 | Put them all together in PDF for submission
Website Component (page)
32 | Team Profile
33 | Ideal Job
34 | Tools
35 | Industry Data
36 | IT Work
37 | IT Technologies
38 | Project idea
39 | Group Reflection