## Sheet1
Initial task allocation and schedule |  |  | Manager | Assistant 1 | Assistant 2 | Assistant 3 | ~4/10/2021 (Mon) | Ahmet | ~8/10/2021 (Fri) | ~9/10/2021 Sat) | ~10/10/2021 (Sun) | ~12/10/2021 (Tues) | ~14/10/2021 (Thurs) | ~15/10/2021 (Fri) | ~16/10/2021 (Sat) | 17/10/2021 (Sun)
|  | Report Component | [5 empty] | Brandon
|  | Team Profile | [5 empty] | Hugo
|  | Team Name | [5 empty] | Taylen
5 | 1 | Organise the team to decide a Team name | Tetsu |  |  |  | Complete the draft | Tim |  | Complete the task | [6 empty] | scrap data from previous assignment and present in unified format
|  | Personal information | [5 empty] | Tetsu
| 2 | Obtain and summarise one paragraph per person including name, student number, background, hobbies, IT interest and IT experience | Tetsu
Team profile
| 3 | Obtain and summarise the test outcomes for each person in the team (all 3 tests) | Tetsu
| 4 | Summarise our understanding of how this information may be helpful to the group | Tetsu
Ideal Jobs
| 5 | Compare and Contrast the ideal jobs for each person in the group | Tetsu
10 |  | Tools (Including Website Compnent)
| 7 | Decide the basic style, format and layout of the website and share with the group | Taylen | Tim |  |  | Complete GitHub set up. Complete the basic layoout and website theme |  | Obtain feedback | Update the website based on the feedback |  | Insert contents |  |  | FInal Check | Submission | style guide
| 8 | Put the website together and submit it as our website for the assignment | Taylen | Tim
| 9 | Create links to each individual website on the group website | Taylen | Tim | [12 empty] | will set-up the templates for the website and future reportings
| 10 | Set up group in Canvas | Taylen | Tim
| 11 | Set up a GitHub repository for the group | Taylen | Tim
| 12 | Include a brief description of what we have done in the report | Taylen | Tim
10 |  | Industry Data
| 13 | Read (and ask the team to read) industry data supplied by Burning Glass and obtain the feedback | Hugo |  |  |  | Complete the draft |  |  | Complete the task
| 14 | Determine the job titles for our group's ideal jobs | Hugo
| 15 | Summarise and report set of skills required for these jobs | Hugo
| 16 | Write in our report if our opinion of ideal job changed? Why or Why not? | Hugo
15 |  | IT Work
| 17 | Decide to interview an IT Professional or pick 10 YouTube videos or web sources | Brandon |  |  |  | Shcedule the interview and draft list of queries |  | Complete the interview | Complete the task (Transcript and Recording) | [6 empty] | Everybody gives questions + one or two people "conduct" the interview
| 18 | Organise and prepare for an interview | Brandon
| 19 | Record an interview | Brandon
| 20 | Include raw transcripts/recordings in appendix to support our written component | Brandon
| 21 | Report on 5 different IT professions as well as indicate 10 sources | Brandon
25 |  | IT Technologies | [14 empty] | Name: | Taylen | Brandon | Tetsu | Timothy | Hugo | Ahmet
| 22 | Report on 4 of the areas (1,200 words @ 4 = 4,800 words) | Ahmet | Ahmet | Ahmet | Hugo | Ahmet to draft at least 1 st area (possibly 2) |  | Ahment to draft 2nd area | Ahmet to draft 3rd area. Hugo to draft 4th area |  |  | Complete the task |  |  |  | Strengths: | Html/coding | Formal Writing | Academic study | formal writing & research | Written Skills | Typewriting
[18 empty] | analytics | Understanding Technical Terminology | Research | adapability | Critical Analysis/Being a Soundboard | Formal Writing Research
15 |  | Project ideas
| 23 | Discuss, determine and brainstorm the group's project idea | Tim |  |  |  | Complete the brainstorming and planning |  |  | Complete the draft |  |  | Complete the task |  |  |  | Weaknesses: | Formal Writing | Management | English writing | Will be slower with html | Coding
| 24 | Write the result in our report | Tim | [14 empty] | Design principles | Delegating | IT skills in general |  |  | Distraction
Coding
7.5 |  | Feedback-SparkPLUS | [14 empty] | Preferred managment: | Website Design | Happy to do anything, I may struggle on the Project Idea aspect as the one mentioned on my 1st Assessment wouldn't be viable in a group assessment. | I am happy to do anything left but not IT work as I cannot think of anyone to interview. | Happy to adapt around the team | Genuinely happy to do anything. Coding/Github are not my strengths but happy to assist where I can. Probably useful everywhere but "tools" | I can write all the four reports for IT areas
| 25 | Supervise members to log in SparkPlUS Tool | Tetsu |  |  |  | whole group | [8 empty] | Complete & Submit
| 26 | Supervise members to complete feedback | Tetsu
7.5 |  | Group Reflection |  |  |  |  | whole group
| 28 | Supervise and obtain each member's perception of the group (200 words each) | Tetsu | [6 empty] | Complete the draft |  |  | Complete the task
| 29 | Write the group reflection as a whole (400 words) | Tetsu
5 |  | Report Completion (Inlcuding design component)
| 30 | Proof reading | Brandon | Hugo | Ahmet |  |  |  | Review Team Profile, Industry Data & IT Technologies 1 | Review IT Technologies 2 | Review IT Technologies 3&4. Review Project Idea. Review Group Reflection |  | Final Check & Collation
| 31 | Put them all together in PDF for submission | Brandon | Hugo | Ahmet | [10 empty] | Submission
100
Website Component (page)
| 32 | Team Profile
| 33 | Ideal Job
| 34 | Tools
| 35 | Industry Data
| 36 | IT Work
| 37 | IT Technologies
| 38 | Project idea
| 39 | Group Reflection
|  | Tetsu | 20
|  | Taylen | 10
|  | Brandon | 20
|  | Hugo | 16.25
|  | Ahmet | 18.75
|  | Tim | 15
100